## Detailed_Bug_Report
Bug ID | Title | Module | Severity | Priority | Status | Release | Business Impact | Proposed Fix
BUG-001 | Crash on corrupted PDF | PDF Parser | Critical | High | Open | P1 | User blocked from analysis | Add try-except
BUG-002 | No file size validation | Upload | Major | High | Open | P1 | Performance degradation | Limit upload size
BUG-003 | Unsupported file acceptance | Upload | Major | Medium | Open | P2 | Unexpected behavior | Validate format
BUG-004 | Duplicate skill scoring | Scoring | Major | Medium | Open | P2 | Incorrect score | Remove duplicates
BUG-005 | Missing loading spinner | Frontend | Minor | Low | Open | P3 | Poor UX | Add loader
BUG-006 | Generic recommendations | Feedback | Minor | Low | Open | P3 | Less useful feedback | Personalize output
BUG-007 | Invalid emails accepted | Validation | Minor | Medium | Open | P2 | Bad data quality | Regex validation
BUG-008 | No score breakdown | Results | Minor | Low | Open | P3 | Reduced transparency | Show details
BUG-009 | No report download | Reports | Minor | Low | Open | P3 | Limited usability | Export PDF
BUG-010 | Formatting not analyzed | Analyzer | Minor | Low | Open | P3 | Incomplete assessment | Analyze layout